## Simple Gantt Chart - BLANK
PROJECT TITLE | Showroom Project | Fill In
PROJECT MANAGER | Sarah Pfeiffer | Fill In
COMPANY NAME | CBRE | Fill In | [5 empty] | Denotes Critical Path - Would any tasks in Section 3 be considered part of the critical path? | [26 empty] | No | Answer
DATE | 2024-07-18 | Fill In
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE
TASK | TASK | TASK | START | DUE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
ID | TITLE | OWNER | DATE | DATE | IN DAYS | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Planning
1.1 | Define scope of Showroom | Project Team 1 | Week 1 | Week 3 | 10
1.1.1 | Research teams to be involved | Project Team 1 | Week 2 | Week 2 | 5
1.2 | Work up initial budget projections | Project Team 1 | Week 2 | Week 3 | 5
1.3 | Final Scope Review | Project Team 1 | Week 3 | Week 3 | 5
1.4 | Create Risk Management Register | Project Team 1 | Week 3 | Week 3 | 2
2 | Project Launch and Execution
2.1 | Create Project Plan via Gantt Chart | Project Team 1 | Week 4 | Week 4 | 5
2.2 | Obtain Building Permit | Project Team 1 | Week 5 | Week 6 | 10
2.3 | Vendor/Supplier Start Work | Project Team 1 | Week 7 | Week 7 | 3
2.3.1 | Vendor 2 Gas Installation | Project Team 1 | Week 7 | Week 7 | 3
2.4 | Appliances Installed | Project Team 1 | Week 7 | Week 7 | 2
2.5 | Final Punch List Created | Project Team 1 | Week 8 | Week 8 | 5
3 | Project Performance / Monitoring
3.1 | Project Objectives | Project Team 1 | Week 1 | Week 8 | 40
3.2 | Effort and Cost Tracking | Project Team 1 | Week 3 | Week 9 | 30
3.3 | Project Performance | Project Team 1 | Week 1 | Week 9 | 45
Project Conception and Planning
Project Launch and Execution
Project Performance / Monitoring
Vendor 2 Gas Installation
Appliances Installed
Vendor/Supplier Start Work
Obtain Building Permit
Final Punch List Created
Yes
No