## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 10 mi | 67% | 40% | 26.67% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 6 mi | 50% | 50% | 0% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% | 31.82% | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 30 mi | 44% | 35.29% | 8.824% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 | 2 | 2 | 40% | 40% | 40% | No new substations completed. Delay in electrical components impacts schedule.
| Spent | Pending
Budget | 90000 | 35000
Component | Completed Units % (Previous) | Completed Units % (This Week)
Track Electrification | 35.29% | 8.824%
Substations Construction | 40% | 40%

## Dashboard
Metroville Urban Rail Expansion Project Dashboard
| Track Installation Progress |  | Electrification Infrastructure Completion Rate | Monies Expended |  |  |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Phase 1
| 70.5% |  | 42% | 90M |  |  |  | Phase 2
Phase 3
Phase 4
PHASE 1
| Progress - Completion % | [11 empty] | Project Financials
| Status Update |  |  |  | Challenges
|  | Completed an additional 6 miles of electrification |  |  | Eastern section in risk
[5 empty] | - Delay |  | due to rocky terrain - 6 mi behind schedule
[5 empty] | ACTION: |  | in progress evaluation of alternative method to
|  | Installed 4 miles of track in the Southeastern Quadrant |  |  | expedite progress
[5 empty] | - Overspent |  | in the excavation
[5 empty] | ACTION: |  | Savings on materials have offset this, keeping us
within 5% of our overall budget projection for this phase
Substation construction
[5 empty] | - Delay |  | in electrical components
[5 empty] | ACTION: |  | action plan in progress with Buyer
| Community Feedback Highlights |  |  |  |  | Relevant Risks
|  | Community appreciates the transparency and opportunity to voice concerns. |  |  |  | Environmental. Unforeseen geological or soil conditions affecting construction
|  | Noise concerns with night construction. Community is requesting limiting work to daytime hours. |  |  |  | Financial. Budget overrun due to cost increases
Financial. Supply chain impacts from delays in delivery of materials
Add electrification progress
Add budget tracking